

FREERIDE COMPETITION MEDIA PRODUCTION COORDINATOR

THE CALLING 2018

A MOUNTAIN SNOWMOBILE FESTIVAL and NON-PROFIT FUNDRAISER

|  |  |  |
| --- | --- | --- |
| SKADI FoundationBox 362Revelstoke BC V0E 2S0 |  | skadifoundation@gmail.comhttp://www.skadifoundation.com |

Table of Contents

1. [The Calling Profile 2](#_Toc489458203)

[Mission Statement](#_Toc489458204)

[Objectives](#_Toc489458205)

[Organizational Chart](#_Toc489458206)

1. [Activity Profile 4](#_Toc489458207)
2. [Coordinator Roles and Responsibilities 4](#_Toc489458208)
3. [Contacts Sheet 5](#_Toc489458209)
4. [Timeline and Activity Schedules 6](#_Toc489458210)
5. [Budget 11](#_Toc489458211)
6. [Marketing 12](#_Toc489458212)
7. [Legal and Liability Management 13](#_Toc489458213)
8. [Policies 14](#_Toc489458214)

[Code of Conduct](#_Toc489458215)

[Policies in Review](#_Toc489458216)

1. [Risk Management 15](#_Toc489458217)
2. [Site Plan 17](#_Toc489458218)
3. [Equipment 19](#_Toc489458219)
4. [Contractors 19](#_Toc489458220)
5. [Volunteers 20](#_Toc489458221)
6. [Sponsors 21](#_Toc489458222)
7. [Stakeholders and Community Resources 21](#_Toc489458223)
8. [Additional Notes 21](#_Toc489458224)

# The Calling Profile

## Mission Statement

*The Calling* is an annual snowmobiling festival in Revelstoke, British Columbia that generates funding for non-profit groups, shifts the culture of safe backcountry mountain motorized use practices, generates community revenue and exposure for Revelstoke as a world-class snowmobiling destination.

## Objectives

The objectives of *The Calling* are as follows:

* Establish an annual snowmobiling festival in Revelstoke, BC specific to the winter sport community that includes a prestigious Cross Country Snowmobiling Race, Vendor Village, Freestyle Demonstrations, Education Clinics and Entertainment.
* Devise a strict Risk Management Plan that includes an effective Emergency Response Plan; these plans should set a new precedence in the industry and be used as a legacy for succeeding winter sport events.
* Raise funds for local non-profits.
* Provide educational opportunities that direct a shift in the culture of safe backcountry mountain motorized use practices.
* Work with local volunteers and clubs to achieve an inclusive community event.
* Use community resources wherever possible to generate community revenue.
* Cross-market Revelstoke, British Columbia and Canada as a world-class snowmobiling destination.
* Maximize marketing opportunities for sponsors and stakeholders.

## Organizational Chart

Attached Organization Chart.



# Activity Profile

The Freeride Competition Media Production Coordinator collects and produces festival Freeride Competition content for: live feeds, web and social media updates, tournament documentation, edits for presentations, media to be used post festival. Teams should have access to HD cameras, Go-Pros, drones and possibly a helicopter. The Freeride Competition Media Production Coordinator works closely with the Marketing Coordinator to ensure content is consistent with *The Calling’s* Marketing Plan.

# Coordinator Roles and Responsibilities

The Coordinator works directly with the Festival Coordinator. The following is a summary of the Coordinator’s responsibilities:

* Design a proposal that meets the requirements outlined in the Activity Profile and follows *The Calling’s* objectives and Coordinator Package Template.
* The Coordinator of the winning proposal must make any changes required by the Boards in accordance with their contract and resubmit their package for final approval. The Festival Coordinator is then responsible for forwarding the approved package to the Executive Administration Assistant and relevant Coordinators indicated in each section of the package.
* Ensure the Festival Coordinator, Executive Administrative Assistant and relevant Coordinators indicated in each section of the package are immediately notified regarding changes to the package leading up to the festival and during the festival.
* Submit detailed schedules for all persons involved with their Activity.
* The Coordinator is required to attend the daily Morning Safety/Operations Meetings and Safety/Operations Debrief Meetings during the festival.
* Provide a general budget for their Activity.
* Work within the Legal and Liability Management outline provided by *The Calling* and provide insight on potential Legal and Liability Management issues within their area of responsibility.
* Submit the Risk Assessment Package for their Activity and work within the Risk Management outline provided by the Backcountry Safety Coordinator.
* Appoint a designated emergency response lead at the site of their Activity who in the event of an Emergency follows the steps outlined in the Emergency Procedures Insert at the front of the final Coordinator Package.
* The Coordinator must contract, supply and is responsible for equipment required to conduct their Activity.
* The Coordinator must hire and is responsible for sub-contractors required to conduct their Activity.
* Collect and provide feedback for Festival Debrief Meeting.
* The Coordinator must ensure their Activity is conducted in compliance with *The Calling’s* Code of Conduct and Policies*.*

# Contacts Sheet

The Coordinator must submit a Contacts Sheet for persons involved in their Activity. The Festival Coordinator, Executive Administration Assistant and the Backcountry Safety Coordinator must be notified immediately if changes are made to the Contacts Sheet.

|  |
| --- |
| **FREERIDE COMPETITION MEDIA PRODUCTION COORDINATOR****CONTACTS SHEET** |
| **Name** | **Role** | **Email** | **Phone** |
| (enter later) | Executive Administrative Assistant | (enter later) | (enter later) |
|  | Festival Coordinator |  |  |
|  | Cross Country Race Director |  |  |
|  | Freeride Competition Director |  |  |
|  | Avalanche Awareness and Riding Clinics Director |  |  |
|  | Photo and Video Challenges Director |  |  |
|  | Social Events Coordinator |  |  |
|  | Marketing Coordinator |  |  |
|  | Communications Director |  |  |
|  | Merchandise Director |  |  |
|  | Website Director |  |  |
|  | Social Media Director |  |  |
|  | Media Production Coordinator |  |  |
|  | Base Camp Media Production Director |  |  |
|  | Backcountry Media Production Director |  |  |
|  | Freeride Competition Media Production Coordinator |  |  |
|  | Base Camp Coordinator |  |  |
|  | Base Camp Safety Coordinator |  |  |
|  | Backcountry Safety Coordinator |  |  |
|  | Volunteers Coordinator |  |  |
|  |  |  |  |
|  | (Additional contacts may be entered later) |  |  |
|  | Contractor |  |  |
|  | Freeride Competition Photographer |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

# Timeline and Activity Schedules

The Coordinator must submit schedules for all persons involved in their Activity. The Festival Coordinator, Backcountry Safety Coordinator, Executive Administrative Assistant and Marketing Coordinator (relevant information) must be notified immediately if changes are made to the timeline and schedules.

|  |
| --- |
| **THE CALLING 2018 PROJECT****DEVELOPMENT/IMPLEMENTATION TIMELINE****2017-2018** |
| 2017Project DevelopmentBudgetsFundraisingCommunicationsSchedulingImplementationMonitoringProblem Management | * May-Sep: PHASE 1 – BUDGET DEVELOPMENT
* Complete Draft 3 of Operations and Business Plans
* Coordinators/Directors submit proposals; upon acceptance revisions required by Board
* Fill all positions
* Definitive Budgets (+10% to -10% accuracy)
* Finalize Coordinator/Director Packages
* Jul-Sep: PHASE 2 – FUNDRAISING STRATEGY
* Team Meeting
* Fundraising Strategies Brainstorm Session
* Team Resources and Skills Assessment
* Establish Sponsorship Structure/The Calling 2018 Branding
* Media Development for fundraising strategies
* Strategy Launches
* Jul-Sep: PHASE 3 – COMMUNICATIONS
* Team Communication Strategies/Templates
* Stakeholder Communication Strategies/Templates
* Media Communication Strategies/Templates
* Jul-Sep: PHASE 4 – SCHEDULING
* Work Breakdown Structures, GANTT Charts, Milestones Chart (visually easy to follow)
* Deadlines, follow-up, accountability, monitoring
* Status Updates and Status Reports
* Sep-Dec: PHASE 5 – IMPLEMENTATION
* Deposits to Coordinators/Directors
* Booking
* Permits/Government Approvals
* Public Consultations
* Vital Services Meetings
* Policy Development
* Launch Marketing Strategy
* Sep-Dec: PHASE 6 – MONITORING
* Follow-up
* Team and Stakeholder Communications
* Sep-Dec: PHASE 7 – PROBLEM MANAGEMENT
* Assist team with staying on track
 |
| 2018ImplementationMonitoringProblem ManagementClosing | * Jan-Mar: PHASES 5-7
* Jan: Confirm contractors and rentals
* Feb: Plan review and last-minute corrections
* Mar: Festival set-up and take-down
* Mar-Apr: PHASE 8 – CLOSING
* Apr: Appreciation to Volunteers, Stakeholders, The Calling Members and Contractors
* Apr: Festival Debrief and develop The Calling 2019 Plan
* May: Present The Calling 2019 Plan to Stakeholders
 |

|  |
| --- |
| **FREERIDE COMPETITION MEDIA PRODUCTION COORDINATOR** **DEVELOPMENT/IMPLEMENTATION TIMELINE****2017-2018** |
| Activities that need to be included in Timeline | * Work with Exec Admin Team on Policy Development
* Meet with Backcountry Safety Coordinator to develop Risk Management Plan
* Work with Backcountry Safety Coordinator to establish clearly defined routes, develop maps (design, layout), safety team requirements, barrier and pylon requirements
* Submit backcountry safety equipment (avalanche transceiver, probe, shovel, airbag) request to Backcountry Safety Coordinator
* Submit Volunteers Request to Volunteers Coordinator
* Submit safety gear, radios, barriers and pylons request to Base Camp Safety Coordinator
* Meet with Marketing Coordinator to develop/pick-up/distribute marketing content
* badges and identifiers, feed link to connect to on the Freeride Competition webpage, working group webpage (location and schedules for working groups).
* Meet with Base Camp Coordinator and Website Director to establish strategy for Freeride Competition live feeds
* Hire professional photographer responsible for Freeride Competition photographs/videos for post festival and real-time content for webpage and social media updates. Provide photographer with boundary maps, schedules and Risk Management Plan.
 |
| 2017 | * Aug
* Submit Proposal, complete required adjustments
* Sep
* Attend Fundraiser Meeting
* Oct
* Nov
* Dec
 |
| 2018 | * Jan
* Confirm contractors and rentals
* Feb
* Plan review and last-minute corrections
* Mar
* Conduct Volunteer Briefing Meeting with volunteers scheduled to work within your area of responsibility
* Collect/distribute badges and identifiers from Marketing Coordinator
* Collect and distribute safety gear and radios from Base Camp Safety Coordinator
* Collect and distribute avalanche safety equipment from Backcountry Safety Coordinator
* Apr
* Collect Feedback
* Collect/return safety gear and radios to Base Camp Safety Coordinator
* Collect/return avalanche safety equipment to Backcountry Safety Coordinator
* Attend Festival Debriefing Meeting
 |
| As at XXX, 2017 |

|  |
| --- |
| **DAILY FREERIDE COMPETITION MEDIA PRODUCTION SCHEDULE****COORDINATOR****March 29 – April 2, 2018** |
| Thursday, March 29 | * 7:00am - 8:00am: Festival Set-up Meeting
* 1:00pm - 2:00pm: *The Calling* Members Meeting
* 5:00pm - 6:00pm: Media Production Teams (3) Meeting
 |
| Friday, March 30STATBad Weather: Tournament Schedule to Saturday | * 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Festival Operations Meeting (8-9) and Free Breakfast
* 10:00am - 5:00pm: Freeride Competition
* 5:00pm - 6:00pm: Opening Ceremony
* 6:00pm - 7:00pm: Festival Recap
* 6:00pm - 7:00pm: Rider Introductions and Meet and Greet
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| Saturday, March 31Bad Weather: Tournament Schedule to Sunday | * Friday riding schedule if weather was unstable
* 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Festival Operations Meeting (8-9) and Free Breakfast
* 10:00am - 5:00pm: Freeride Competition
* 6:00pm - 7:00pm: Festival Recap
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| Sunday, April 1 | * Saturday riding schedule if weather was unstable
* 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Festival Operations Meeting (8-9) and Free Breakfast
* 10:00am - 5:00pm: Freeride Competition
* 5:00pm - 6:00pm: Closing Ceremony and Awards
* 6:00pm - 7:00pm: Festival Recap
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| Monday, April 2 | * 8:00am - 9:00am: *The Calling* Members and Stakeholders Meeting
 |
| As at XXX, 2017 |

|  |
| --- |
| **DAILY FREERIDE COMPETITION MEDIA PRODUCTION SCHEDULE****FREERIDE COMPETITION PHOTOGRAPHER****March 29 – April 1, 2018** |
| Friday, March 30STATBad Weather: Tournament Schedule to Saturday | * 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Free Breakfast
* 10:00am - 5:00pm: Freeride Competition
* 5:00pm - 6:00pm: Opening Ceremony
* 6:00pm - 7:00pm: Festival Recap
* 6:00pm - 7:00pm: Rider Introductions and Meet and Greet
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| Saturday, March 31Bad Weather: Tournament Schedule to Sunday | * Friday riding schedule if weather was unstable
* 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Free Breakfast
* 10:00am - 5:00pm: Freeride Competition
* 6:00pm - 7:00pm: Festival Recap
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| Sunday, April 1 | * Saturday riding schedule if weather was unstable
* 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Free Breakfast
* 10:00am - 5:00pm: Freeride Competition
* 5:00pm - 6:00pm: Closing Ceremony and Awards
* 6:00pm - 7:00pm: Festival Recap
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| As at XXX, 2017 |

|  |
| --- |
| **DAILY FREERIDE COMPETITION MEDIA PRODUCTION SCHEDULE****VOLUNTEER****March 30 – April 1, 2018** |
| Friday, March 30STAT | * 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Festival Operations Meeting (8-9) and Free Breakfast
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| Saturday, March 31 | * 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Festival Operations Meeting (8-9) and Free Breakfast
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| Sunday, April 1 | * 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Festival Operations Meeting (8-9) and Free Breakfast
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| As at XXX, 2017 |

|  |
| --- |
| **DAILY FREERIDE COMPETITION MEDIA PRODUCTION SCHEDULE****CONTRACTOR****March 30 – April 1, 2018** |
| Friday, March 30STAT | * 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Festival Operations Meeting (8-9) and Free Breakfast
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| Saturday, March 31 | * 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Festival Operations Meeting (8-9) and Free Breakfast
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| Sunday, April 1 | * 7:00am - 8:00am: Festival Safety Meeting
* 8:00am - 10:00am: Festival Operations Meeting (8-9) and Free Breakfast
* 7:00pm - 8:00pm: Safety/Operations Debrief Meeting
 |
| As at XXX, 2017 |

# Budget

The budget of $XX,XXX has been allocated to this area of responsibility. The Coordinator must provide a general breakdown of projected expenses for the Activity. Include in-kinds and potential receivables.

The budget in this area of responsibility may include: Coordinator salary,

Items supplied by other areas of responsibility include: marketing materials indicated in Marketing section supplied by Marketing Coordinator; safety gear, radios, barriers and pylons supplied by Base Camp Safety Coordinator; Safety Teams supplied by Backcountry Safety Coordinator; Swag Bag contents supplied by Base Camp Coordinator; spare backcountry safety equipment (avalanche transceiver, probe, shovel, airbag) for working groups and participants supplied by the Backcountry Safety Coordinator.

# Marketing

Marketing for this area of responsibility is supplied by the Marketing Coordinator. Items in the Marketing Plan specific to this area of responsibility include: badges and identifiers, feed link to connect to on the Freeride Competition webpage, working group webpage (location and schedules for working groups).

The Coordinator must submit a request for marketing materials, provide content, and notify the Marketing Coordinator of any incorrect or updated information for the website and social media regarding their area of responsibility.

It is an objective of *The Calling* to maximize marketing opportunities for sponsors and stakeholders. The Coordinator must provide insight to and submit requests to the Marketing Coordinator for marketing opportunities within their area of responsibility for example: promotions, cross-marketing and merchandise.

# Legal and Liability Management

The Coordinator must work within the Legal and Liability Management outline provided by *The Calling.* The Coordinator must provide insight on potential Legal and Liability Management issues within their area of responsibility.

Potential Legal and Liability Management within this area of responsibility include:

* Role Contract
* Collect required copies for due diligence: waivers (participant, sub-contractors, volunteers), contracts, certificates, permits, licenses, sub-contractor WCB clearance letters
* Radio Use Permit
* Drone Permit
* Liability Insurance
* Waive rights to photo/video edits
* Helicopter: Noise Bylaw, Permits

# Policies

## Code of Conduct

Members of *The Calling*, Contractors and Volunteers actively representing *The Calling* must behave in a professional, safe manner and act in the best interest of *The Calling*. Alcohol consumption and drug use is detrimental to *The Calling’s* vision of providing a safe, community event and is not acceptable.

## Policies in Review

The following policies are in review for this area of responsibility:

# Risk Management

It is an objective of *The Calling* to devise a thorough Risk Management Plan that includes an effective Emergency Response Plan. Risk Assessment Packages assist Safety Coordinators in the development of Risk Management Plans and ensure Vital Service requirements are in place at each Activity. The following plans are explored in the Risk Assessment Package: Master Site Plan, Medical Plan, Security Plan, Public Health Plan, Fire Safety Plan, Communications Plan, Traffic Management Plan, Liquor Control Plan, Other Contingency Plans.

The Backcountry Safety Coordinator will assist with developing and finalizing the Risk Assessment Package for this area of responsibility. The Coordinator must work within the finalized Risk Management Plan provided by the Backcountry Safety Coordinator. The Coordinator must appoint a designated emergency response lead at the site of the Activity who in the event of an emergency follows the steps outlined in the Emergency Procedures Insert (provided by the Backcountry Safety Coordinator) at the front of the final Coordinator Package. The Festival Coordinator, Backcountry Safety Coordinator and the Executive Administration Assistant must be notified immediately if changes are made to the Risk Management Plan.

The following planning considerations will be reviewed in the Risk Assessment Package for this area of responsibility:

### Medical Plan

The Freeride Competition Media Production Coordinator provides a service to the Freeride Competition. The Freeride Competition Risk Management Plan should include the services the Freeride Competition Media Production Coordinator provides.

### Security Plan

security risk assessment, communications protocol

### Public Health Plan

The Freeride Competition Media Production Coordinator provides a service to the Freeride Competition. The Freeride Competition Risk Management Plan should include the services the Freeride Competition Media Production Coordinator provides.

### Fire Safety Plan

The Freeride Competition Media Production Coordinator provides a service to the Freeride Competition. The Freeride Competition Risk Management Plan should include the services the Freeride Competition Media Production Coordinator provides.

### Communications Plan

designated communications lead, communication devices

### Traffic Management Plan

The Freeride Competition Media Production Coordinator provides a service to the Freeride Competition. The Freeride Competition Risk Management Plan should include the services the Freeride Competition Media Production Coordinator provides.

### Other Contingency Plans

weather, evacuation plan, delay/cancellation protocol, emergency response protocol

Additional Risk Management within this area of responsibility include: Coordinator must attend Morning Safety/Operations Meetings and evening Safety/Operations Debrief Meetings, constant contact with Freeride Competition Safety Team, timed interval check-in log, Freeride Competition Safety Team to respond in the event of an Emergency.

# Site Plan

The Site Plans for areas where the Freeride Competition Media Production Team is deployed will be provided by the Freeride Competition Director. Copies should be provided here.

{INSERT MAP HERE}

# Equipment

It is an objective of *The Calling* to use community resources wherever possible to generate community revenue. The Coordinator must contract, supply and are responsible for equipment needed to conduct their Activity. The cost for equipment is outlined in the budget.

Equipment required in this area of responsibility may include: HD Cameras, Go-Pro Cameras, Drones

# Contractors

It is an objective of *The Calling* to use community resources wherever possible to generate community revenue. The Coordinator is responsible for hiring Contractors. Contractors hired must be in good standing with WCB. The Coordinator must collect insurance, waivers and other pertinent documents from their Contractors and submit copies to the Festival Coordinator for proof of due diligence. A list of potential/confirmed Contractors should be provided here.

Contractors required in this area of responsibility may include:

# Volunteers

It is an objective of *The Calling* to achieve an inclusive community event; Coordinators are encouraged to access volunteers and community groups wherever possible. Coordinators must submit a Request for Volunteers to the Volunteers Coordinator and include the information sampled in table below. For liability and security purposes all volunteers must be registered by the Volunteers Coordinator.

The Volunteers Coordinator recruits and schedules volunteers, ensures relevant waivers and Criminal Record Checks are completed, and collects copies of required certifications and licenses. Volunteers must not be given money or gift certificates for their services. The Coordinator may contact the Volunteers Coordinator if a scheduled volunteer does not show up for their shift.

A list of potential/confirmed Volunteer opportunities should be provided here.

|  |
| --- |
| **REQUEST FOR VOLUNTEERS** |
|  | **General Job Description** | **Requirements** | **Safety Gear/****Certificates/Licenses** |
| **Freeride Competition Media Production** |  |  |  |
| Staging Area Assistant (2) | Help outfit and organize participants | {What days/hours?} | Vests |
|  |  |  |  |

Volunteer opportunities for this area of responsibility may include:

Volunteers to be requested by the Backcountry Safety Coordinator may include: members of the Safety Team.

# Sponsors

It is an objective of *The Calling* to maximize marketing opportunities for sponsors and stakeholders. The Coordinator must provide a list of sponsor marketing opportunities within their Activity.

Sponsor Opportunities for this area of responsibility may include:

# Stakeholders and Community Resources

The Coordinator must provide a list of stakeholders and organizations that may be effected by or could provide insight to their Activity and may need to be solicited.

Stakeholders that may be effected by this area of responsibility may include:

# Additional Notes

**© 2017 SKADI Foundation ALL RIGHTS RESERVED**

Plans contained in this document are owned and protected by SKADI Foundation. No part may be reproduced in the development of a similar event without prior written permission from SKADI Foundation. No part of this work may be reproduced or used in any form or by any means – graphic, electronic, or mechanical, including photocopying, recording, taping, or information storage and retrieval systems – without prior written permission from SKADI Foundation.

SKADI Foundation

Box 362

Revelstoke BC V0E 2S0

skadifoudation@gmail.com

http://www.skadifoundation.com

Writer: Jeremy Hanke

Writer/Editor: Misty Bergquist

Contributors: Craig Moore, Duncan Lee, Emily Roberts, Erik Luzak, Jaclyn Moore, Jeff Scott, Mark Karlstrom,

Robert Sim, Scott Wickson